## Project Plan
KNOWLEDGE BASE BUILDER (GRAPH-RAG & MULTI-AGENT ARCHITECTURE)
Actions (Modules) | Sub-actions (Tasks) | Module Type
1. Requirement Gathering | Source system identification: Define Azure Blob storage structures, directory paths, and plan API scopes/auth for Confluence/Wiki integration. | KB
| Finalize ingestion functional scope for CSV, Excel, PDF, DOCX, Markdown, TXT, JSON, and XML schemas. | KB
| Map business knowledge domains (SAP docs, Incident RCAs, Playbooks, SOPs, Historical logs) to data taxonomy. | KB
| Document interaction and functional metrics (Total Documents, Data Processed, Active Pipelines, Total Knowledge Stores). | KB
2. Architecture Design | Design End-to-End microservices architecture blueprint (Ingestion, Processing, Embedding, Graph, Retrieval, Orchestrator, UI etc). | Both
| Define Knowledge Pipeline technical specs: metadata semantic enrichment strategies and chunking boundaries. | KB
| Finalize database architectures: Define OpenSearch indexing schemas and NetworkX graph traversal/clustering workflows. | KB
| Model the Feedback & Correction Loop: Formulate state transitions and memory management for Investigator and Editor agents. | KB
3. Infrastructure & Codebase Setup | Set up GitHub repository structure, branching strategy, CI/CD basic templates, and monorepo/microservices layout (airflow-dags/, ingestion-service/, etc.). | Both
| Code base bootstrapping: Write core configuration modules (config/settings.py, core/models.py), logging helpers, and standard exception handlers. | Both
| Secure .env configuration mapping across all key environments (Azure connection strings, Event Grid, OpenSearch, OpenAI/Claude API keys). | Both
4. Data Source Layer | Develop Azure Blob Storage connector with folder traversal, recursive polling, and support for incremental file sync. | KB
| Build REST connector integration for scheduled content synchronization. | KB
| Implement early-stage data classification routers to distinguish and label structured, unstructured, and semi-structured payloads. | KB
5. Airflow Orchestration Pipeline | Write core Apache Airflow DAGs for scheduled, triggered, and incremental ingest pipelines. | KB
| Configure tasks dependency management, automatic exception retries, and error alerting integrations. | KB
| Build monitoring hooks within Airflow to track document processing stages and orchestrate downstream embedding/graph tasks. | KB
6. Intelligent Document Processing | Build file-downloading and temporary disk-staging layer for multi-threaded document retrieval. | KB
| Write native parsing engines for tabular formats (Excel, CSV) and raw text/unstructured files (PDF, DOCX, Markdown, TXT). | KB : Heavy
| Implement JSON/XML data parsing rules to extract semi-structured metadata. | KB
| Build Document Classification engine utilizing LLM zero-shot or pattern matching for Intent, Domain, and Metadata extraction. | KB
7. Metadata & SQLite Database Layer | Code the database schemas via SQLAlchemy ORM mapping out the structural tables. | KB
| Develop migrations and CRUD repository methods to handle transactional status changes for chunks and assets. | KB
8. Knowledge Pipeline | Design advanced chunking strategies: implement semantic chunking, recursive token-aware splitting, and context overlap preservation rules. | KB
| Integrate OpenAI embedding generator layer with integrated fallback, rate-limiting handlers, and token counters. | KB
| Build the Graph creation pipeline: implement entity extraction, relationship schema mapping, and domain/community identification via NetworkX. | KB : Heavy
9. Knowledge Base Layer | Provision and set up OpenSearch cluster schemas, configuring precise vector indices and similarity metrics (e.g., Cosine/L2). | KB
| Implement real-time metadata filtering support directly inside vector search profiles. | KB
| Develop Graph Database layer using NetworkX to execute community-based clustering algorithms and relationship-based traversal logic. | KB
10. Retrieval Layer | Build the Hybrid Retrieval Engine combining BM25 keyword matching with OpenSearch Vector Semantic search. | KB
| Write Graph-based retrieval mechanics to fetch surrounding node networks for conversational context expansion. | KB
| Develop hybrid ranking logic (e.g., RRF - Reciprocal Rank Fusion) with Top-K optimization and duplicate context removal filters. | KB
| Expose unified, latency-optimized Retrieval APIs to serve downstream orchestrators. | KB
11. RAG API Orchestrator | Code the multi-model RAG orchestrator routing layer supporting Azure OpenAI GPT, Claude, or Llama integrations. | KB
| Implement user query pre-processing, context assembly templates, and prompt augmentation layers. | KB
| Build safety guardrails: incorporate hallucination prevention checks, strict source-grounded response logic, and confidence scoring. | KB
| Build citation enforcement filters and multi-turn conversation memory session-tracking mechanisms. | KB
12. Interactive Chatbot UI | Scaffold the Next.js Frontend app, configuring global states, dark/light themes, and custom streaming components. | UI
| Build conversational chat container supporting real-time token streaming and message markdown rendering. | UI
| Develop Advanced UI features: Side-by-side Source Citation panel, expandable text chunks, and visual graph relationship dashboards. | UI : Heavy
| Build knowledge exploration dashboards with multi-tier category-based filtering and analytics tracking. | UI
13. Feedback & Correction Loop | Build UI submission forms for feedback, incorrect retrieval reporting, and suggested correction triggers. | UI / Agent
| Implement Investigator Agent workflow to process user feedback and analyze underlying root-cause chunking/retrieval flaws. | Agent : Heavy
| Implement Editor Agent workflow to automatically modify relevant database chunks or update local metadata properties. | Agent : Heavy
| Code the human-in-the-loop SME Review and validation workflow, blocking direct updates until administrative approval is flagged. | Agent / UI
14. Testing | Write Unit tests for all core business backend microservices, embedding functions, and API endpoints. | Both
| Execute System Integration Testing (SIT) focusing on end-to-end Airflow-to-DB pipelines and agentic feedback loops. | Both
| Conduct User Acceptance Testing (UAT) focusing on UI interaction smoothness, streaming response rates, and citation accuracy. | Both
15. Deployment & Handover | Package applications via Docker and deploy multi-container deployments onto Azure Kubernetes Service (AKS) with HPA autoscaling. | Both
| Configure infrastructure health checks, live performance metrics monitoring, and production-ready log streaming. | Both
| Execute comprehensive Knowledge Transfer (KT) sessions and hand over detailed pipeline architectural documentation. | Both
TOTAL ESTIMATED EFFORT